# MODERNIZATION EQUIPMENT ACQUISITION PROGRAM

## Quarterly Status Brief — Q4 FY2024

## Program Office: Modernization Equipment Acquisition (MEA) Distribution: Program Office Staff, Government Oversight Date: December 2024

## Program Health Snapshot

## Overall Status: YELLOW

## 1 of 4 subsystems at Red — Propulsion

## 2 of 4 subsystems at Yellow — Navigation, Power Distribution (closed Green end of quarter)

## 1 of 4 subsystems at Green — Communications

## Schedule: 6-week slip to system integration test (SIT) entry. New SIT date: March 2025.

## Budget: On track overall. Propulsion subsystem approaching full expenditure ($1.19M of $1.2M allocated).

## Propulsion — RED

## Vendor: Apex Defense Systems

## Turbine seal issue unresolved as of Dec 2024

## Corrective action plan (CAP) issued Q2; partially effective; escalated Q4

## 30-day cure notice issued 2024-11-02

## Root cause: Single-source supplier unable to meet tolerance spec

## Impact: SIT entry delayed 6 weeks

## Budget: $1,190,000 of $1,200,000 expended (99%)

## Next action: Cure notice response due 2024-12-02. PM to assess response and determine path forward.

## Risk: If cure not satisfied — contract termination and re-procurement under evaluation as contingency

## Navigation — YELLOW

## Vendor: Meridian Technologies

## Firmware timing conflict identified Q3; root cause confirmed Q4

## Patch in development; delivery expected Q1 FY2025

## No hardware changes required — software fix only

## Lab testing paused pending patch delivery

## Budget: $910,000 of $950,000 expended (96%)

## Next action: Patch delivery and regression test Q1 FY2025

## Risk: If patch delayed beyond Feb 2025 — risk escalates to Red; SIT further impacted

## Communications — GREEN

## Vendor: Consolidated Systems Inc.

## Hardware fabrication complete

## No open risks

## Delivery for integration testing confirmed Q1 FY2025

## CDR findings (Q3): both closed within 30 days — no residual issues

## Budget: $795,000 of $800,000 expended (99%)

## Next action: Coordinate integration test scheduling with propulsion team

## Note: Integration test sequencing dependent on Propulsion SIT resolution

## Power Distribution — GREEN

## Vendor: Apex Defense Systems

## Single-source capacitor bank risk retired Q3 FY2024

## Alternative supplier qualified; risk formally closed

## No open risks

## Budget: $590,000 of $600,000 expended (98%)

## Next action: Interface testing with Propulsion subsystem — schedule TBD pending SIT resolution

## Note: Propulsion slip has downstream impact on Power Distribution integration sequencing

## Key Risks (Open)

| ## Risk ID | ## Subsystem | ## Description | ## Likelihood | ## Impact | ## Status |
| --- | --- | --- | --- | --- | --- |
| ## R-001 | ## Propulsion | ## Turbine seal supplier unable to meet spec | ## High | ## High | ## Open — Cure Notice Issued |
| ## R-002 | ## Navigation | ## Firmware patch delivery delayed past Feb 2025 | ## Medium | ## High | ## Open — Monitoring |
| ## R-003 | ## Program | ## Propulsion slip cascades to SIT and downstream milestones | ## High | ## High | ## Open — Schedule revised |

## Closed Risks (This Quarter)

| ## Risk ID | ## Subsystem | ## Description | ## Closure Date |
| --- | --- | --- | --- |
| ## R-004 | ## Power Distribution | ## Single-source capacitor bank supplier | ## Q3 FY2024 |

## Upcoming Milestones

| ## Milestone | ## Subsystem | ## Planned Date | ## Status |
| --- | --- | --- | --- |
| ## Cure Notice Response | ## Propulsion | ## 2024-12-02 | ## Pending |
| ## Firmware Patch Delivery | ## Navigation | ## Q1 FY2025 | ## On Track |
| ## Comms Hardware Delivery | ## Communications | ## Q1 FY2025 | ## On Track |
| ## System Integration Test Entry | ## All | ## March 2025 | ## AT RISK |

## Actions Required

## PM: Assess Apex cure notice response by 2024-12-05 and brief SSA

## Contracts: Prepare re-procurement package as contingency (due 2024-12-15)

## Engineering: Confirm SIT entry criteria with revised March 2025 date

## Meridian Technologies: Deliver firmware patch no later than 2025-02-01